## Toolkit Intro
Getting Started Toolkit
Tool | Description
1. ASSET INVENTORY
User Guide
How to develop an inventory for asset management | An overview of what information should be included in an asset inventory, where to get the information from, and how to use your TCA inventory to build an asset management inventory.
Tools
Asset inventory field descriptions | A list of fields in an asset inventory with descriptions and examples.
Sample asset codes | Categories and sub-categories of codes that can be used in asset inventories.
Asset inventory template | An editable sample template for developing an asset inventory for asset management.
2. LEVELS OF SERVICE
User Guide
How to define levels of service | A description of a process for defining levels of service with basic and anecdotal information.
Tools
Level of service template | An editable sample worksheet for documenting levels of service.
Level of service example | An example completed level of service worksheet.
3. RISK MANAGEMENT
User Guide
How to manage risks | A description of a process for the management of risks. This process is applicable to both asset and strategic risks.
How to assess asset risks | A description of a process for identifying and ranking asset risks with basic and anecdotal information.
How to assess strategic risks | A description of a process for identifying and ranking strategic risks.
Tools
Sample consequence and likelihood table | An example of consequence and likelihood definitions.
Asset risk register template | An editable template for recording and ranking risks to service delivery.
Risk register example | An example completed risk register.
4. COSTS
User Guide
How to understand costs | A description of the process of understanding costs and what needs to be included.
Tools
Asset replacement forecast summary template | An editable template for a summary level asset replacement forecast.
Capital plan template | A basic editable template for a ten year capital plan.
5. IMPLEMENTING ASSET MANAGEMENT
User Guide
How to develop a first asset management plan | A sample outline for an asset management plan.
Implementing asset management through the budget process | How to incorporate considerations of service, risk, and cost throughout the budget process.
Implementing asset management through the community planning process | How to incorporate considerations of service, risk, and cost into master planning and municipal development plans.
Implementing asset management through public communication and engagement | Incorporating asset management information into community surveys and annual reports.
6. CONTINUOUS IMPROVEMENT
User Guide
How to assess and improve your asset management practices | A process for conducting an assessment of asset management practices and a template for planning for improvement.
Overview of asset management resources | A review of the major publicly available asset management resources that identifies the scope and focus of each resource.

## INVENTORY->
ASSET INVENTORY TOOLS
- Asset Inventory Field Descriptions
- Asset Inventory Template

## Inventory Field Descriptions
Asset Inventory Field Descriptions
| Field | Description | Example | Notes
What do we own? | Asset Codes | The code, or class for the type of asset. | Engineered structures - xxx Water - W | Your TCA register may use asset classes, so you may choose to use the same ones. You may also choose to assign different codes based on the department structures or budget alignment. You may have a sub-class as well.
| Asset ID | Unique identifier for the asset | xxx.xxxxxxx.xx | May be automatically generated by software or assigned based on a system.
| Asset Extension | An extension on the unique identifier | .xx | You may use an extension when retiring and replacing an asset with a new asset.
Where is it? | Location | The physical location of the asset. This may be coordinates of the asset, or may be described as two points (from x to y) for linear assets. | From 1st Ave & Main St. to 2nd Ave. & Main St. | May represent this information in GIS. Not all of these descriptors are required - choose what makes sense for you.
| Municipal Address | The municipal address of where the asset is fixed or stored. | 123 Main Street
| Legal Description | Legal description of the land where the asset is fixed or stored. | Lot 16, Block 4, Plan 804 3167
What are the attributes? | Material | The material the asset is made from | PVC | For assets made of more than one material, record the predominant material or separate the asset into component parts (e.g. base and surface for a road)
| Quantity | The amount of the asset (length, size, volume, etc.) | 108
| Quantity units | The units the quantity is measured in | m
| Year Installed | The year the asset was installed or acquired | 1987
| Year Renewed | The year of major renovation or renewal that will extend the life of the asset. | 2006 | Put N/A for assets that have not had renewals conducted.
| Age | The current year minus the date of installation | 28
| Make | The manufacturer of the asset |  | Required for equipment and vehicles only
| Model | Model of the asset |  | Required for equipment and vehicles only
What will it cost to replace? | Historic cost | The cost of the asset when it was acquired. | 15000 | Include cost of design. For contributed assets, use estimated cost based on unit rates. This information is optional, and not required for asset management.
| Replacement unit cost | Cost per unit to replace, in the same unit as the quantity. | 325 | Can be based on recent projects or on publicized rates. May not be relevant for all asset types.
| Replacement value | Total quantity multiplied by the replacement unit cost. | 35100
What condition is it in? | Physical condition rating | A rating of the physical condition of the asset | May be Failed/Poor/Fair/Good, or may be a specific number based on assessment | For all condition ratings, use a system based on the data that you have.
| Functional condition rating | A rating of whether the asset is functioning as intended.
| Demand condition rating | A rating of whether the asset is meeting the required demand.
How long will it last? | Expected service life | Theoretical service life of the asset | 50
| Remaining service life | Estimated number of years until the asset fails | 40 | This may be based on the expected service life and the age, or based on actual renewal, performance and condition data.
| Remaining service life basis | How service life was estimated | Expected life/ actual condition
Source of information | Sources | List of sources of information | List all relevant sources of information
| Accuracy | Notes about the accuracy of information | Rating of the accuracy of information, highlighting areas that need to be improved.
Example Categories
Major
[5 empty] | Code | Category
[5 empty] | W | Water
[5 empty] | S | Sanitary
[5 empty] | D | Storm
[5 empty] | R | Roads
Minor
[5 empty] | Code | Sub- Category
Water lines
[5 empty] | P | Main
[5 empty] | SL | Service Line
Water Points
[5 empty] | HYD | Fire Hydrant
[5 empty] | FT | Fitting
[5 empty] | PV | Pressure Reducing Valve
[5 empty] | NS | Pumphouse (Pump, lift, transfer stations)
Reservoir
Treatment Plant
Water Tank
Truck Fill
Meter Chamber
[5 empty] | FM | Flow Meter
[5 empty] | CV | Control Valve
[5 empty] | SS | Sampling Station
[5 empty] | V | Valve
Sanitary Lines
[5 empty] | FM | Forcemain
[5 empty] | P | Pressure Main
[5 empty] | MN | Main
[5 empty] | SV | Service Line
Sanitary Points
[5 empty] | CO | Cleanout
[5 empty] | NS | Lift Station
Lagoons
[5 empty] | MH | Manhole
[5 empty] | VL | Valve
[5 empty] | TP | Treatment Plant
[5 empty] | AR | Air Relief Valve
[5 empty] | MR | Flow Meter
[5 empty] | PU | Pump Station
Drainage Lines
[5 empty] | CU | Culvert
[5 empty] | DI | Ditch
[5 empty] | P | Main
[5 empty] | SV | Service Line
Drainage Points
[5 empty] | MH | Manhole
[5 empty] | CB | Catch Basin
[5 empty] | LS | Lift Station
[5 empty] | OUT | Outfall
[5 empty] | WET | Wetlands
[5 empty] | DP | Detention Pond
Roadways Lines
[5 empty] | LN | Lanes
[5 empty] | RD | Roads
Roadway Points
[5 empty] | BD | Bridges
[5 empty] | CRB | Curb and Gutter
[5 empty] | MU | Multi-Use Path
[5 empty] | SW | Sidewalk
[5 empty] | SN | Road Signs
[5 empty] | SL | Street Lights
[5 empty] | TL | Traffic Lights

## Inventory Template
Inventory Template
What do we own? |  |  |  | Where is it? |  |  | What are the attributes? | [8 empty] | What does it cost? |  |  | What condition is it in? |  |  | How long will it last? |  |  | Data Source and Accuracy
Asset Description | Asset Code | Asset ID # | Asset Ext. | Location | Municipal Address | Legal Description | Material | Quantity | Units | Year Installed | Year Renewed | Service Life | Age | Make | Model | Historic Cost | Replacement Unit Cost | Replacement Cost | Physical Condition | Functional Condition | Demand Condition | Expected Service Life | Estimated Remaining Life | Remaining Life Source | Soruce of Information | Accuracy
Total
Feasibility Total
Design and Contingencies Total

## LEVELS OF SERVICE->
LEVELS OF SERVICE TOOLS
- Level of Service Template
- Level of Service Example

## LOS Template
Level of Service
Date updated:
Completed by: |  | Note: this template links level of service and cost
Service Category: |  | Annual service area budget:
Assets providing services:
Major asset components | Replacement value | Expected remaining life | Condition
Primary customer groups:
CUSTOMER LEVELS OF SERVICE
Service attributes that matter to customers | Current performance | Desired performance (current) | Type of Adjustment Required
ASSET PERFORMANCE INDICATORS
Asset | Indicator | Current performance | Desired performance
OPERATIONS AND MAINTENANCE ACTIVITIES REQUIRED TO DELIVER SERVICES
Current O&M activities | Current annual cost | Adjustment required | Cost impacts
New O&M activities | Rationale |  | Cost impacts
Capital Projects | Estimated cost impacts | Priority (H,M,L) | Notes/considerations
Information Type | Source | Accuracy | Improvements required
STEP 1
STEPS 6 & 7
STEPS 3, 4,& 5
STEP 2
STEP 9

## LOS example
Level of Service - Example
Date updated: | 2015-09-01
Completed by: | Team member names | Note: this template links level of service and cost
Service Category: | Recreation | Annual service area budget:
Assets providing services: | 1 Leisure centre with swimming pool, 1 skating arena
Major asset components | Replacement value | Expected remaining life | Condition
Leisure centre building |  | 20 years | Fair
Pool equipment |  | 5 years
Arena building |  | 15 years
Arena equipment |  | 15 years | Excellent
Primary customer groups: | General public, teams, school groups
CUSTOMER LEVELS OF SERVICE
Service attributes that matter to customers | Current performance | Desired performance (current) | Type of Adjustment Required
Facilities are open reliably | Unexpected closures are very rare | Maintain | None
Facilities are clean | Very few customer complaints re: cleanliness | Maintain | None
Facilities are in good repair | Some complaints regarding paint chipping and general worn appearance | Improve | O&M - paint facility and increase frequency of minor repairs
Facilities are uncrowded | Fair/Poor - ice arena is consistently booked and does not meet demand | Improve | Capital - new facility required
ASSET PERFORMANCE INDICATORS
Asset | Indicator | Current performance | Desired performance
Leisure centre building | Facility physical condition | Fair | Good
Pool equipment | Equipment breaks and downtime | Good | Good
Arena building | Facility physical condition | Fair | Good
Arena equipment | Equipment breaks and downtime | Good | Good
OPERATIONS AND MAINTENANCE ACTIVITIES REQUIRED TO DELIVER SERVICES
Current O&M activities | Current annual cost | Adjustment required | Cost impacts
Daily cleaning | 40000 | maintain | 0
Quarterly pool equipment service | 28000 | maintain | 0
Quarterly arena equipment service | 28000 | maintain | 0
Quarterly facility repairs | 16000 | increase frequency to bi-monthly | Estimated add'l $4,000/year
Summary of adjustments required |  |  | +$4,000/year
New O&M activities | Rationale |  | Cost impacts
Annual roof cleaning and inspection | Roof is aging and condition needs to be monitored |  | Additional $6,000/year
Capital Projects | Estimated cost impacts | Priority (H,M,L) | Notes/considerations
Build new arena | 700000 | Medium | Will have O&M impacts
Paint facility | 8000 | High | Planned for 2016
Information Type | Source | Accuracy (H,M,L) | Improvements required
Performance information | Anecdotal | Medium | The condition of the pool equipment should be inspected as it nears its expected end of life.

## RISK MANAGEMENT->
ASSET RISK ASSESSMENT PROCESS TOOLS
- Sample consequence and likelihood tables
- Asset risk register template
- Example risk register
STEP 3: Beginning with categories related to the high level objectives, develop Consequence Table that outlines the specific definitions for each of the categories. Should be developed with a team to ensure concensus among those who will be conducting the assessment or using the results.
STEP 1: Select Asset System (i.e. roads, water, wastewater, etc.)
STEP 2: Identify high level objectives for asset system (i.e. safety, accessibility, etc.)
STEP 4: As a team, identify undesirable events, ocurrences, or conditions that may hinder the ability of the assets to deliver intended services.
STEP 5: Using the consequence table and likelihood definitions, assign a score for consequence and likelihood for each event. Record the scores in the risk register.
STEP 6: Calculate the risk score (likelihood x consequence) for each event, and sort the risk register from the highest to lowest risk score.

## Consequence and Likelihood
Sample Consequence Table - ROADS
| Category | 1 | 2 | 3 | 4 | Weight | Notes
| Operational Impacts | Requires semi annual monitoring or repair | Requires monthly monitoring or repair | Requires weekly monitoring or repair | Unable to maintain or operate OR repair requires greater than one week | 0.6 | Reactive operational effort above what is routine
| Environment | Short term irritant (i.e. Dust) | Prolonged irritant (i.e. Dust) OR Aesthetic impact | Release of deleterious substances to environment (i.e. Hydraulic fluid, diesel fuel, etc.) | Release of deleterious substances to environment that result in a fine | 0.8 | O&G, fines to waterway, etc. Dust control Noise
| Safety | Near miss | Minor injuries that do not require medical consultation | Injuries require medical consultation | Many people with major injuries OR fatality | 1 | Consider all road users - pedestrians, bikes, vehicular. Roads, lights, signs, etc.
| Travel Time | Travel time is increased for a period of < 48 hours | Travel time is increased for a period of 48 hours - one month | Travel time is increased for period of one month - four months | Travel time is increased for period of > four months | 0.6
| Accessibility | Short term access interruption <10 mins (no alternate route) OR less than 10 households | Short term access interruption 10 min - 1 hour | access interruption 1 - 24 hours | Service interruption to emergency services OR >24 hours | 0.8 | Access to residences, goods, services, emergency services, other civic services. High weight. Assumption - no alternate route (if there is an alternate route, this is captured under Travel Time)
| Service Delivery - Comfort | Minor decrease in ride comfort and increase in noise levels | Moderate decrease in ride comfort and noise levels. Obstructions visible but alteration in path and speed are not required. | Decreased speed required. Occaisional alteration of path. | Frequently alter driving path. Vehicle damage. Major decrease in ride comfort and noise level | 0.8
| Reputation | One off localized negative publicity | Short term regionalized negative publicity | Prolonged regionalized negative publicity | Prolonged major reputation damage, prolonged reports in national news | 0.4
| Financial | <$5k | >$5k-$100k | $100k-$1M | >$1M | 0.8 | Reactive costs
Sample Likelihood Table
| Likelihood | 1 | 2 | 3 | 4
|  | Improbable | Possible | Likely | Almost Certain
|  | Could happen, but probably never will except under exceptional circumstances | The event might occur at some time as there is a history of this event occuring | There is strong possibility of this event occuring as there is a frequent history of occurence | Very likely. Expected to occur in most circumstances.
Ranking Matrix
Likelihood | Consequence
|  | 1 | 2 | 3 | 4
| 1 | 1 | 2 | 3 | 4
| 2 | 2 | 4 | 6 | 8
| 3 | 3 | 6 | 9 | 12
| 4 | 4 | 8 | 12 | 16
NOTE: Refer to a worked example in the Toolkit Guide for more on how to develop the weighting system and assess risks.

## Risk Register Template
Risk Register
Assessment Scope
| Date Last Modified: |  |  |  | Note: Scores are given between 1 and 4 (lowest to highest). Each category holds a weighting from 0 - 1. | [7 empty] | Consequence | Likelihood |  | Risk Treatment
Number | Undesirable Event | Why? | Why? | Consequence - Notes | Operational Impacts | Enviro | Safety | Travel Time | Access | Service Delivery - Comfort | Reputation | Financial | Weighted Consequence Score | Score | Risk Score | Current Mitigating Actions | Possible Mitigating Actions | General Notes
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!
[13 empty] | #VALUE! |  | #VALUE!

## Risk Register - example
Risk Register - Example
| Assessment Scope | Roads
| Date Last Modified: | 2015-04-23 |  |  |  | Note: Scores are given between 1 and 4 (lowest to highest). Each category holds a weighting from 0 - 1. | [7 empty] | Consequence | Likelihood |  | Risk Treatment
Number | Undesirable Event | Why? | Why? | Why? | Consequence - Notes | Operational Impacts | Enviro | Safety | Travel Time | Access | Service Delivery - Comfort | Reputation | Financial | Weighted Consequence Score | Score | Risk Score | Current Mitigating Actions | Possible Mitigating Actions | General Notes
[6 empty] | 0.6 | 0.8 | 1 | 0.6 | 0.8 | 0.8 | 0.4 | 0.8
3 | Road xyz - gravel portion failure | Designed as a rural road with minimal traffic. |  |  | It would have an impact on accessibilty for residents living in the area. | 3 | 1 | 1 | 1 | 4 | 3 | 2 | 4 | 13.8 | 3 | 41.4 | Regular grading of roadway. | Upgraded by area developer.
5 | ABC Blvd Blockage | Caused by traffic congestion and poor design. |  |  | Increased traffic congestion and prolonged wait times at traffic lights. | 1 |  | 1 | 1 | 2 | 3 | 3 | 3 | 9.8 | 4 | 39.2 | Traffic timing changes. | Marina Rd Highway 1A intersection upgrade.
8 | Premature Failure of Road 5 | used for construction Road was not upgraded to accomadate for increased volumes of traffic. |  |  | Complete road closure. | 2 |  | 1 | 3 | 4 | 2 | 2 | 3 | 12 | 3 | 36 | Road weight restrictions have been placed on the roadway. Also an assesment is currently underway on 241A. | Rebuild roadway
1 | Mountain Road - increase congestion due to new subdivision development | One of the primary roadways connecting South East Mountainville to the rest of the Town. |  |  | Increased usage may result in traffic congestion and degraded condtion. | 1 |  | 1 | 4 | 2 | 3 | 3 | 2 | 10.8 | 3 | 32.4 | Monitoring | Upgrade Range Road 282 to provide another viable option for commuters. Look into any long range transportation plans.
7 | Failure of annexed roads | increased truck traffic | increased volume |  |  |  |  | 1 | 3 |  | 3 |  | 3 | 7.6 | 4 | 30.4 | Maintenance. Collect offsite levies to recover costs | Introduce weight and speed restrictions. | Financially not possible to reconstruct the road
2 | Flooding on south rural roads | poor drainage, inadequate design | standing water on either side of the roads - natural drainage is poor |  | More frequent monitoring. Would require significant repair after water receedes. Turbidity to wetlands | 4 | 3 |  | 3 |  |  |  | 2 | 8.2 | 3 | 24.6 | Reactive repair. Spring preventative repair | Install culverts, improve drainage. Redesign - pave roads | Traffic patterns will change with development
11 | Congestion at the intersection of Valley Road and River Drive | Increased adjacent development | Design |  | Permanent congestion - car vs. Pedestrian. As development increases, problem will amplify |  |  | 1 | 4 |  |  | 3 |  | 4.6 | 4 | 18.4 | Monitoring | Have discussed phasing of the lights on Chestermere Blvd and Windermere. Has been evaluated. Redesign traffic patterns in commercial area.
6 | Premature failure of existing roads - south east quadrant | Original construction estimate was low | Difficult site conditions for construction | Kinniburgh - shortage of funds to complete the extension | Access to medical centre, highschool. If don't build it, will need to upgrade other areas |  |  |  |  | 2 |  | 1 | 4 | 5.2 | 3 | 15.6 | Construction of extension - on the books | Decrease load rating, reduce speed, reconstruct roads (require assessment) | Kinniburgh expansion
4 | Flooding on major collector | trap low on major collector | Poor erosion and sediment controls upsteam |  |  | 3 |  |  |  | 1 |  | 2 |  | 3.4 | 4 | 13.6 | CUI visits the site during all major rain events to monitor the site | Subdivision design submissions should be carefully reviewed to ensure trap lows are properly placed and stormwater management is properly designed
9 | Main Bridge Closure - prolonged | Structural failure |  |  |  | 4 |  | 1 | 4 |  |  | 3 | 4 | 10.2 | 1 | 10.2 | Alberta Transportation is currently conducting bridge repair. Bridge inspections every 56 months. | Weight and speed restrictions. Reviewing monitoring procedures after the repair is done.
2 | Traffic light failure on highway | power outage | accident or snowplow damage | increased construction - new signals require alteration of existing | Collision |  |  | 2 | 1 |  |  |  |  | 2.6 | 2 | 5.2 | Routine maintenance | Inspections of construction. Installing bollards. Speed restriction.

## COSTS->
COST AND FUNDING TOOLS
- Asset Inventory Field Descriptions
- Asset Inventory Template

## ARF - Asset Category Example
Asset Replacement Forecast - Example for Roads
Physical Details | [15 empty] | Cost Information - BASE | [5 empty] | Replacement Cycles |  | Cost Information - SURFACE | [5 empty] | Replacement Cycles |  |  |  | Funding Needs and Timing | [19 empty] | Budget Requirements
Asset _ID | Road Name | From | To | ACRES Roadway Classification | Roadway Category | Width (m) | Length (m) | Year Renewed Surface | Year Renewed Base | Service Life Surface | Service Life Base | Revised Service Life Surface | Revised Service Life Base | Age Surface | Age Base | Unit Cost | Replacement Value | Loss in Value | Remaining Value | Expected Remaining Life | Infrastructure Deficit (Backlog) | 1st | 2nd | Unit Cost | Replacement Value | Loss in Value | Remaining Value | Expected Remaining Life | Infrastructure Deficit (Backlog) | 1st | 2nd | 3rd | 4th | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 20 Year Total | Average Annual Life Cycle Investment (AALCI)
OIBDC
Roads-Campground
R-001 | None |  |  | Rural Local | 3 | 7 | 243.845 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 63240.8482 | 27667.8711 | 35572.9771 | 56.25% | 0 | 2060 | 2140 | 25 | 42672.8674 | 42672.8674 | 0 | 0% | 42672.8674 | 2015 | 2042 | 2069 | 2096 | 42672.8674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42672.8674 | 2370.9872
R-002 | Unknown |  |  | Rural Local | 3 | 7 | 93.7727 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 24319.8101 | 10639.9169 | 13679.8932 | 56.25% | 0 | 2060 | 2140 | 25 | 16410.2168 | 16410.2168 | 0 | 0% | 16410.2168 | 2015 | 2042 | 2069 | 2096 | 16410.2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16410.2168 | 911.7834
R-003 | Unknown |  |  | Rural Local | 3 | 7 | 72.7549 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 18868.889 | 8255.1389 | 10613.7501 | 56.25% | 0 | 2060 | 2140 | 25 | 12732.1126 | 12732.1126 | 0 | 0% | 12732.1126 | 2015 | 2042 | 2069 | 2096 | 12732.1126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12732.1126 | 707.4208
R-004 | Unknown |  |  | Rural Local | 3 | 7 | 260.7944 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 67636.6565 | 29591.0372 | 38045.6193 | 56.25% | 0 | 2060 | 2140 | 25 | 45639.0159 | 45639.0159 | 0 | 0% | 45639.0159 | 2015 | 2042 | 2069 | 2096 | 45639.0159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45639.0159 | 2535.7921
R-005 | Unknown |  |  | Rural Local | 3 | 7 | 321.977 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 83504.2811 | 36533.123 | 46971.1581 | 56.25% | 0 | 2060 | 2140 | 25 | 56345.9729 | 56345.9729 | 0 | 0% | 56345.9729 | 2015 | 2042 | 2069 | 2096 | 56345.9729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56345.9729 | 3130.6914
R-006 | Unknown |  |  | Rural Local | 3 | 7 | 317.6973 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 82394.3537 | 36047.5297 | 46346.8239 | 56.25% | 0 | 2060 | 2140 | 25 | 55597.03 | 55597.03 | 0 | 0% | 55597.03 | 2015 | 2042 | 2069 | 2096 | 55597.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55597.03 | 3089.0787
R-007 | Unknown |  |  | Rural Local | 3 | 7 | 95.8517 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 24858.9965 | 10875.811 | 13983.1855 | 56.25% | 0 | 2060 | 2140 | 25 | 16774.0423 | 16774.0423 | 0 | 0% | 16774.0423 | 2015 | 2042 | 2069 | 2096 | 16774.0423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16774.0423 | 931.9983
R-008 | Unknown |  |  | Rural Local | 3 | 7 | 150.4483 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 39018.5453 | 17070.6136 | 21947.9317 | 56.25% | 0 | 2060 | 2140 | 25 | 26328.4453 | 26328.4453 | 0 | 0% | 26328.4453 | 2015 | 2042 | 2069 | 2096 | 26328.4453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26328.4453 | 1462.8594
R-009 | Unknown |  |  | Rural Local | 3 | 7 | 139.2274 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 36108.4226 | 15797.4349 | 20310.9877 | 56.25% | 0 | 2060 | 2140 | 25 | 24364.7892 | 24364.7892 | 0 | 0% | 24364.7892 | 2015 | 2042 | 2069 | 2096 | 24364.7892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24364.7892 | 1353.7549
R-010 | Unknown |  |  | Rural Local | 3 | 7 | 64.1939 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 16648.5917 | 7283.7589 | 9364.8328 | 56.25% | 0 | 2060 | 2140 | 25 | 11233.9282 | 11233.9282 | 0 | 0% | 11233.9282 | 2015 | 2042 | 2069 | 2096 | 11233.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11233.9282 | 624.1788
R-011 | Unknown |  |  | Rural Local | 3 | 7 | 93.1944 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 24169.8328 | 10574.3019 | 13595.531 | 56.25% | 0 | 2060 | 2140 | 25 | 16309.0171 | 16309.0171 | 0 | 0% | 16309.0171 | 2015 | 2042 | 2069 | 2096 | 16309.0171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16309.0171 | 906.1606
R-012 | Unknown |  |  | Rural Local | 3 | 7 | 101.7262 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 26382.5395 | 11542.361 | 14840.1785 | 56.25% | 0 | 2060 | 2140 | 25 | 17802.0796 | 17802.0796 | 0 | 0% | 17802.0796 | 2015 | 2042 | 2069 | 2096 | 17802.0796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17802.0796 | 989.118
R-013 | Unknown |  |  | Rural Local | 3 | 7 | 72.7145 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 18858.4075 | 8250.5533 | 10607.8542 | 56.25% | 0 | 2060 | 2140 | 25 | 12725.04 | 12725.04 | 0 | 0% | 12725.04 | 2015 | 2042 | 2069 | 2096 | 12725.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12725.04 | 707.0279
R-014 | Unknown |  |  | Rural Local | 3 | 7 | 92.8826 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 24088.9606 | 10538.9203 | 13550.0404 | 56.25% | 0 | 2060 | 2140 | 25 | 16254.4472 | 16254.4472 | 0 | 0% | 16254.4472 | 2015 | 2042 | 2069 | 2096 | 16254.4472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16254.4472 | 903.1286
R-015 | Unknown |  |  | Rural Local | 3 | 7 | 99.1855 | 1980 | 1980 | 27 | 80 | 27 | 80 | 35 | 35 | 37.0498 | 25723.628 | 11254.0873 | 14469.5408 | 56.25% | 0 | 2060 | 2140 | 25 | 17357.4675 | 17357.4675 | 0 | 0% | 17357.4675 | 2015 | 2042 | 2069 | 2096 | 17357.4675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17357.4675 | 964.4145
Sub-total | [6 empty] | 2220.2656 | [9 empty] | 575822.763 | 251922.4588 | 323900.3042 | 56.25% | 0 |  |  |  | 388546.4719 | 388546.4719 | 0 | 0% | 388546.4719 |  |  |  |  | 388546.4719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388546.4719 | 21588.3946

## ARF - Summary Level
Asset Replacement Forecast - Summary Template
Physical Details |  |  | Funding Needs and Timing | [39 empty] | Budget Requirements
Asset Category | Replacement Value | Infrastructure Deficit (Backlog) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 40 Year Total | Average Annual Infrastructure Renewal Investment (AALCI)
Water System
Pipe |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Facilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hydrants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Appurtenances |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wastewater System
Pipe |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Treatment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Facilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manholes and Appurtenances |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stormwater System
Pipes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spillway and Appurtenances |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roadway System
Roads |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bridges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Streetlights |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Buildings
Buildings
Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Infrastructure |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Capital Plan Template
Capital Plan
[8 empty] | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Capital Plan Revision:
|  |  | 10 Year Capital Plan: |  |  | 2016-2025 |  | 2015: Population Projection | Date Last Modified:
Funding
| No. | Program | Project Name | Department | Driver | Start Date | Total | 2015: Spending Profile | Total | Municipal | Reserves | Debt | Grant
TOTAL
Projected Funding

## Document Review
Review Key | ISO 55000 Asset management - overview, principles, and terminology By the International Organization for Standardization | ISO 55001 - Asset management - Management systems - Requirements | ISO 55002 - Asset management -Guidelines for the application of ISO55001 | National Guide to Sustainable Municipal Infrastructure - Decision Making and Investment Planning - Managing Infrastructure Assets | National Guide to Sustainable Municipal Infrastructure - Best Practices for Utility-Based Data | National Guide to Sustainable Municipal Infrastructure - Developing a Water Distribution System Renewal Plan | National Guide to Sustainable Municipal Infrastructure - Developing Levels of Service | National Guide to Sustainable Municipal Infrastructure - Public Consultation | Asset Management BC Roadmap and Guide | Canadian Infrastructure Report Card - Infrastructure Primer | International Infrastructure Management Manual (2011) | Asset Management Getting Started Guide - Asset Management Saskatchewan | Asset Management for Sustainable Service Delivery: A BC Framework (Long Version) | Alberta Urban Municipalities Association - Guide for Municipal Asset Management Plans | Ontario Ministry of Infrastructure - Building Together: Guide for Municipal Asset Management Plans | Ontario Asset Management Toolkit
General Description | Is a standard for asset management systems - similar to other management systems (environmental, quality, etc.). Developed for asset intensive businesses, not specific to local government. Provides context for ISO 55001 and ISO55002. Primary focus of the document is AM context and benefits | Specifies the requirements for the components of the asset management system in order to be in compliance with the ISO standard for asset management systems | Explanatory text and some examples to support the stated requirements in ISO55001 | Overview of the components of municipal infrastructure asset management planning and benefits. | A guide for local governments on the identification, storage, and management of utility-based data and information. Focused on water, wastewater, and stormwater utilities. Most useful to those just starting out in developing information management systems. | Reviews both the top-down and bottom-up approach to developing a renewal plan for a water distribution system. | Guide that provides outline of information on the benefits of defining levels of service and how to define them. | Guide that outlines the need for public consultation, the activities that can support, and the level of effort required to conduct. | A document to assist municipalities with implementation of asset management practices at three different levels. The roadmap guide provides details on the "basic" level of asset management. Identifies what is needed but does not prescribe how to get it. | A companion to the Canadian Infrastructure Report Card that describes the relationship between the state of asset management and the results in the Infrastructure Report Card. Includes key recommendations for improvement. | Comprehesive guidance and case studies on the implementation of asset management. Focus on defining the services that assets need to deliver, and then developing lifecycle strategies to effectively deliver service. | Introductory guide describing asset management and where to start. | Framework for implementing asset management that illustrates the ongoing process of asset management. Links to other resources. | Online webpage resource that provides a high-level introduction to asset management, and five individual tools (state of infrastructure; understanding financial position; informed decision making; managing asset lifecycles; and set, review, comply and respond). | Document that provides a background on the Building Together Plan and Municipal Infrastructure Strategy. Also identifies what an asset management plan needs to include. Views AM as a prerequisite to productive discussion about solutions for infrastructure challenges. | Web-based toolkit that includes: communications Tipsheet, Self-assessment checklist, asset inventory tipsheet, sample state of infrastructure reports, risk management primer, lifecycle costing primer, partnerships tipsheet
Basics
What is Asset Management | "Coordinated activity of an organization to realize value from assets." Provides an overview of asset management and asset management fundamentals: Value, Alignment, Leadership, and Assurance. Differentiates between 'asset management' and 'asset management system'. |  |  | Uses definition from US Department of Transport - Asset Management is a systematic process of maintaining, upgrading, and operating physical assets cost-effectively. It combines engineering principles with sound business practices and economic theory, and it provides tools to facilitate a more organized, logical approach to decision-making. Thus, asset management provides a framework for handling both short- and long-range planning." Also identifies key principles of asset management, including asset value, lifecycle management, long-term affordability, risk management and assessment, performance measurement, operational plans, and integration of technical and financial plans. Describes the framework for an asset management plan as the seven questions. | [5 empty] | Provides a definition of asset management based on four fundamentals (Value, Alignment, Leadership, and Assurance) | Provides definition of asset management and key elements. | Includes definition of asset management, identifies infrastructure assets, and what is included in asset management (uses the seven key components from the International Infrastructure Management Manual): Life cycle approach, cost-effective management strategies, defined level of service, demand management, risk management, sustainable use of physical resources, and continuous improvement |  | Describes asset management as a process of managing the lifecycle of assets in a cost effective manner to deliver levels of service. | Includes paragraph to describe asset management as making best possible decisions to maximize benefits, manage risk, and provide satisfactory levels of service to the public in a sustainable manner. | Description of asset management included
Benefits of Asset Management | Identifies benefits of asset management as improved financial performance, informed asset investment decisions, managed risk, improved services and outputs, demonstrated social responsibility, demonstrated compliance, enhanced reputation, improved organizational sustainability, improved efficiency and effectiveness. Identifies benefits that come frome creating an asset management system and moving toward cross-functional integration, even before the system is fully operational - such as new perspectives on value creation, new insights from data collection and increased organizational knowledge. |  |  | Identifies bullet list of specific benefits of asset management | [6 empty] | Includes section on drivers and benefits of asset management | Outlines benefits of asset management |  | Identifies benefits of asset management and of developing an asset inventory. | Maximize the benefits provided by infrastructure. Achieve cost savings, manage risk, optimize investments, prolong infrastructure.
Where to start |  |  | Identifies that there can be benefit in developing the first Asset Management Plan using existing information to better understand strengths and weaknesses. | Does not identify where to start, but does identify what is needed for implementation. | [6 empty] | Section on asset management drivers, understanding and defining requirements. Includes maturity indices for key components of asset management. | Guide is focused on getting started, and includes a specific section for this |  | Presents a cyclical process of five basic steps to developing an asset management plan. | Section 4 identifies a series of actions that can help a municipality start or enhance the asset management planning process.
Definitions | Includes terms and definitions that are used throughout the ISO55000 documents. Identifies relationships between key parts of the AM system. |  |  | Includes a glossary of key terms | Glossary of data mangement related terms |  |  |  | Includes comprehensive glossary of asset management terms. |  |  | Includes definitions for common asset management terms
Asset Data
Asset Inventory/ Register & Attributes |  |  |  | What do you have and where is it? References Infraguide Best Practices for Utility Based Data (2003d) for data collection and management. | Identifies the need for standard referencing systems to enable integration of data and information. Includes a list of standard asset attributes to be collected. |  |  |  | Identifies what an inventory is, why it is needed, and what should be in it. Outlines how to create an asset inventory. Identifying asset components is also included as a building block. |  | Section on establishing base asset knowledge, including identifying asset requirements, structure and hierarchy, asset identification systems, and data collection processes. | Outlines how to develop an asset register using the TCA register developed for PS3150 requirements. How to define segments of infrastructure. |  | Includes a description of an asset inventory. The tool "State of local infrastructure and assets" includes a description of what should be in an asset inventory and an example of an asset hierarchy. | Identifies the role of the asset inventory in backing up the asset management plan. | Asset inventory tipsheet identifies what should be included in the inventory and how to determine the information
TCA (historic cost, amortization), linking TCA and AM
Condition Assessments and Asset Performance Data |  |  |  | What is its condition and expected remaining service life? |  | Provides a detailed list of condition and performance indicators for water distribution systems. Information is in-depth, but only covers water systems. | Identifies the link between understanding the asset and asset performance, and levels of service. |  | Module called Condition Assessment identifies the benefits of collecting condition information and a process for planning the collection of condition information. A list of information to be collected for each asset is included. | Identified the challenge of grading and reporting asset condition in a consistent manner, within and across municipalities. Recommends the use of certain terms (Very Good - Very Poor) and includes definitions to assist categorization into these categories. | Section on assessing asset condition, including processes, techniques, and examples of asset-specific condition grading systems. |  |  | "Managing asset lifecycles" includes information on the benefits of asset condition monitoring, steps to recording and tracking asset condition |  | Inventory tipsheet provides sample asset condition model.
Data collection, management and integration |  | Requirement to document information, ensure appropriate control, updating, and consider the impact of the quality of information on organizational decision making | Considerations for defining information needs, including examples of information to be collected and things to consider in prioritizing information for collection, aligning data, and managing it. Putting controls into place to ensure data is approved, accurate, up to date, and can be used for decision making. | Refer to Infraguide's "Best Practices for Utility-Based data". References need to plan for the effort required to maintain data, and to prioritize data collection. | Primary focus of the document. Identifies the type of data to be collected and stored, how to ensure the accuracy and integrity of data, how to collect and store data, and how to retrieve data in a simple and practical way. Includes principles of data management. Appendices include a checklist for asset management data system checks. |  |  |  |  | Includes a recommendation to document and store information that is currently retained by experienced staff in some type of management system. | Data collection processes outlined in section "Establishing Base Asset Knowledge". Also includes sub-section on maintaining and improving data confidence.
Data storage and software systems |  |  |  | References information technology and the integration between different systems. Emphasis that software is only a tool and that the data is what is most important. | Importance of recognizing the complexities of software systems as tools for data management. Includes a full section on issues regarding computerization. |  |  |  | Includes a module on data knowledge, software and tools. Discusses why knowledge about data, software and tools is necessary, and what information should be documented. |  | Section on "Information Systems and Tools". Information systems are identified as an asset management enabler.
Replacement value |  |  |  | What is it worth? | Recommended asset valuation attributes | Need for considering socio-economic costs as well as infrastructure repair, rehabilitation, and replacement |  |  | Importance of knowing replacement cost and what the information can be used for. Includes basic process for determining replacement cost. |  | Section on Financial and Funding Strategies includes information on valuation approaches and calculating depreciated replacement cost. |  |  | Information sheet on "understanding your municipality's financial position" includes information on determining replacement value. |  | Some information on replacement cost is included in the inventory tipsheet
Natural assets
Financial data, O&M costs, lifecycle costs, etc. |  |  |  |  | Determining the costs of activities |  |  |  | Differentiating between capital, operational, maintenance, and renewal costs. Purpose of tracking O&M costs to optimize decision making about capital investments. Benefits of separating operations and maintenance costs. Overview of how to implement O&M cost recording, and what expenses should be tracked when possible. |  | Information within "Financial and Funding Strategies" section on identifying and categorizing Lifecycle Costs. | Defines what lifecycle costs are and the need for determining them. |  | Information sheet on "understanding your municipality's financial position" includes information on determining depreciated value, best practices on tracking O&M costs, tracking future capital costs. | Importance of having lifecycle costs to inform the selection of actions to deliver levels of service. Identifies the need to track direct and indirect costs. | A primer on lifecycle costing outlines processes for estimating lifecycle costs using discount rates
Information
Risk |  | Requirement to identify risks and their significance | Includes an example method for identifying, analysing, and evaluating risk. Requirement for documenting risk management. | [6 empty] | Highlights the importance of risk management in relation to delivering levels of service. | Section on Identifying Critical Assets and Business Risks |  |  |  |  | Includes risk management primer that provides an overview of risk analysis and provides a risk register template.
Level of Service |  |  |  | What is the level of service expectation? Mentions the need to consider level of service in capital and operational plans, and the need to tie LOS to community priorities. |  |  | Identifies benefits of defining levels of service, outlines steps for defining levels of service, and the link to financial considerations. |  | Describes parameters for level of service and benefits to documenting the levels of service. Roadmap does not specify the method for defining levels of service, but provides considerations for definition. Identifies the importance of estimating the cost of providing levels of service. The module called "Legal Obligations and Standards" is also relevant. | Identifies the need to shift mindset from managing assets to managing service levels. Includes a recommendation that municipalities understand levels of service, and focus on managing assets, risks, and investment decisions in order to deliver service levels. | Section on Developing and Monitoring Levels of Service | Explains the concept of levels of service, how levels of service are used in asset management, the relationship to risk and community consultation. An example for roads is provided. |  | "Managing Asset Lifecycles" includes information on level of service, defining current and desired levels of service, the relationship with cost, and considerations for defining acceptable levels of service. Provides a basic approach for defining levels of service.
Policy | Role of policy - the extent to which an organization intends to achieve its objectives through asset management should be identified in the policy | Requirements for what should be included in an AM Policy | Requirements of a policy, including example policy statements. Considerations for documenting, communicating, and reviewing a policy. | Requirement to identify policy objectives in order to identify how achievement is assessed. Suggests identifying policy objectives in terms of service levels, to define what businesses and residents expect. | [5 empty] | Identifies the importance of having an Asset Management Policy to confirm the organizations commitments and expectations for decisions, activities, and behavior concerning asset management. | Asset Maangement Policy is discussed under "The Strategic Context and the Asset Management Policy"
Strategy | Identifies the role of the Strategic Asset Management Plan (SAMP). | Requirement for the SAMP to identify the role of AM in achieving organizational objectives | Things to consider when developing the asset management objectives and strategy to achieve the objectives. Typical asset management objectives. | Discusses strategy only in the context of defining priorities that guide how funding limitations are dealt with? |  |  |  |  | Includes a module called "Assess asset maintenance strategies", the purpose of having a strategy for maintenance and how to assess asset maintenance strategies. | Identifies the importance of having an Asset Management Strategy that defines objectives and strategies for achieving the Policy requirements. | Referenced under "The Strategic Context and the Asset Maangement Policy" | Includes a diagram that outlines how asset management ties into existing practices and plans. Refers to overall organizational strategic plan, rather than AM strategy. |  | "Set, review, comply, and respond" document includes a description for setting and maintaining strategic goals with a focus on maintenance strategy. | Identifies strategy as a component of the asset management plan, and discusses strategy as a set of actions to deliver levels of service. Defines AM strategy as the sect of actions that, taken together, have the lowest lifecycle cost (rather than the lowest lifecycle cost individually).
Long term capital plan |  |  |  | What is the level of service expectation and what needs to be done? When do you need to do it? Identifies the need to integrate renewal plans across infrastructure types to minimize overall costs and disruption. Does not discuss integration with new projects, focus is on replacement of existing assets. |  | Key questions to consider in cost-benefit analysis to determine the most efficient timing of projects. |  |  | Includes a module called "Assess asset renewal alternatives" which documents the need for a process for assessing alternatives. Module called "Co-ordinating Infrastructure Works" is also relevant |  | Section on "Developing Capital Investment Strategies and Plan" which outlines how to develop the main components of the capital plan. |  |  | Coordinating infrastructure works is listed as a best practice on the "Set, review, comply, and respond" document.
Asset Replacement Plan | [5 empty] | Provides proxy guidelines for water system replacement based on larger group reviews of information. Details both a top-down approach (for long term strategic planning) and a bottom-up approach (for short term capital planning). Identifies the importance of projecting asset renewal requirements at least one full lifecycle ahead. |  |  | Termed "future capital costs". Recommneds 20 year forecast. Identifies benefits to estimating future costs. Outlines a process for determining future capital costs through renewal costs and/or capital new asset costs. |  | Sub-section on "Developing Renewal Programs"
Climate Change
Asset Management Plan / Planning |  | Requirements for determining and documenting in asset management planning | Common components of an Asset Management Plan and considerations for developing plans. | Identifies that an asset management plan should include: key principles, essential elements, data collection, implementation needs, operational considerations, successful implementations, and emerging trends. Framework for an asset management plan is the seven questions. |  |  |  |  | Does not include a specific module on developing an asset management plan, as there are many formats and starting points for developing an asset management plan. The roadmap instead focuses on asset management practices. | Recommends that municipalities develop an Asset Management Plan for the portfolio of assets required to support delivery of services. Includes a suggested outline for an asset management plan. | Section on Asset Management Plans as an Asset Management Enabler. Includes a process for plan development and an example of an asset management plan structure. | Identifies the kind of information an asset management plan should include (expected upcoming infrastructure work, timing and cost of work, current funding in place, discussions about levels of service and risks associated with providing levels of service). |  |  | Provides a list of sections for an asset management plan (executive summary, introduction, state of infrastructure, expected levels of service, asset management strategy, and financing strategy) and contents for each section. Future funding in Ontario is dependent on having all of these sections in an asset management plan.
Finances
Long term financial planning |  |  |  | Identifies the requirement for integrating technical and financial plans. Question - how much will it cost and what is the acceptable level of risk? How do you ensure short and long term affordability? References Infraguide's 2004 Developing a Water Distribution System Renewal Plan document |  | Strategies for paying for long term replacement of infrastructure. |  |  |  |  | "Developing Funding Plans" and " Developing Long Term Financial Forecasts" within "Financial and Funding Strategies" | Identifies how asset management links to long term financial planning, and the importance of reducing potential financial shocks in the future. |  |  | Includes a section on integration with financial planning, identifying a "building blocks approach to determining cost" and the components to be included in the revenue plan. Also outlines the requirements for a financing strategy that aligns with the asset management plan.
Revenue | [8 empty] | Referred to as "Funding Sources". Benefits to knowing funding sources and what this information can help to determine. Highlights the need for collaboration between finance and engineering, and the types of funding sources that should be forecasted. |  | "Developing Funding Plans" within "Financial and Funding Strategies" |  |  | "Understand your financial position" sheet provides best practices on funding levels and sources
Reserves / Restricted Surplus
Financial sustainability benchmarks/ Strategic Planning
Financial Resources for asset management |  | Requirement to resource asset management | Need for an iterative process that reconciles proposed activities with available resources. | [5 empty] | Module included called "Prioritized Improvement Plan" which refers to the need to prioritize AM implementation and to identify the required budget and timeline for each activity. |  |  | Identifies the need for additional time and resources to get started with asset management.
People
Engagement and communication (staff and council) | Recognizes importance of consultation with employees and stakeholders | Identifies what staff need to be aware of, and the requirements of the AM system to identify communication needs | Lists of potential internal and external stakeholders. Lists of what staff should be aware of, and methods for improving organizational awareness. Considerations for developing a communication plan and example content. | If implementing asset management requires changes to process or organizational structure, recommendation to implement change management. Asset management implementation plan should address quick wins first to build buy-in and trust for the process. |  |  | Identifies the role of communication and engagement in defining levels of service. |  | Importance of conducting consultation and communication within council and with staff. Outlines how to approach consultation. |  | "Asset Management Teams" section within "Asset Management Enablers" | Identifies the need for elected officials, administrators, and staff to be engaged in the process, understand the benefits, and buy in to the need to practice asset management. Identifies how both staff and elected officials can use asset management outputs. Includes a list of questions that can be asked of council to determine how familiar they are with the state of infrastructure in their community. |  |  |  | Includes a tipsheet for communicating asset management
Community engagement | [6 empty] | Provides some suggestions for how to engage the community related to Levels of Service and the benefits provided. | Includes principles for consultation, benefits of consultation, steps to take, potential communication tools or approaches, their required level of effort, and how to evaluate the effectiveness of the initiatives. Also includes an appendix on media training. | Importance of consultation and communication with customers and stakeholders. |  | Customer consultation processes included in "Developing and Monitoring Levels of Service" section
Asset management roles/ competencies (incl. council) | Under the fundamental of Leadership, states that leadership and culture are determinants of value and there is a requirement for clearly defined roles, responsibilities, and authorities; ensuring that employees are aware, competent, and empowered. Identifies the role of organizational leaders in AM. | Requirements for leadership to demonstrate leadership and commitment to AM. Identifies which responsibilities need to be assigned. Requirement to ensure necessary competence. | Considerations for assiging responsibilities to roles and requirement to communicate responsibilities to stakeholders. Examples for conducting a gap analysis and training plan for competency improvement. Relationship between competencies and organizational design. | [6 empty] | Recommendation to develop competencies and training strategies that support asset management practices. | Roles, structures, and capability requirements are covered in section on "Asset Management Teams"
Teamwork |  |  |  | Specifies need for a cross-functional team with a designated champion that reports to senior management. | [6 empty] | Section on "Asset Management Teams"
Leadership | requirement for leadership | requirements from leadership | how to demonstrate leadership requirements | [7 empty] | Covered in "Asset Management Teams"
Implementation
Implementing asset management |  | Identifying the scope of the asset management system | Determining the scope of the AM system Consideration of criteria for implementation of processes and actions (e.g. roles and responsibilities, procedures, resource allocation, and competency development). Considerations for management of change. | Differentiates between operational approach and senior-directed approach. Lists needs for implementation (people, information, information technology, computerized asset management system, business plan, implementation plan). Identifies common challenges to implementing asset management - including institutional challenges, technical challenges, and funding challenges. Includes implementation case studies to illustrate different implementation approaches. Suggests modifications for implementing in small or remote municipalities. |  | Identifies the applications and limitations of the top-down and bottom-up approaches. |  | Identifies the role of communication and engagement in implementing asset management. | Outlines a process for implemeting asset management planning using the roadmap. Also includes a module on "Prioritized Improvement Plans" for the implementation of asset management.
Benchmarking, assessment, performance evaluation, reporting | Identifies the importance of performance evaluation | Document lists all the requirements for asset management systems, and can be used as an assessment tool. Requirements of a performance evaluation and reporting, internal auditing, and management reviews for the purposes of compliance with ISO standards. | Requirements for the development of processes for systematic measurment, monitoring, analysis, and evaluation of the organization's assets, asset management system, and asset management activity on a regular basis. Statements on what the process for monitoring performance should address. Requirements for internal audits and management reviews. | Section on evaluating the effectiveness of asset management, including some examples of what can be tracked for evaluation. Identification of two types of benchmarking - metric benchmarking and process benchmarking. References Canadian benchmarking studies, such as the Ontario Municipal Chief Administrative Officers Benchmarking Initiative (OMBI), the Ontario Municipal Performance Measurement Program (MPMP) and the Canadian National Water and Wastewater Benchmarking Partnership. |  | Identifies a list of measures that can be used to evaluate effectiveness of top-down and bottom-up practices. |  |  |  |  | Section on "Continuous Improvement" which includes assessing curent and appropriate AM performance
Continuous improvement | [8 empty] | Module on Improvement Plan and Process. Outlines why an improvement plan is beneficial and a process for developing an improvement plan. |  | Section on "Continuous Improvement" |  |  | "Set, review, comply, and respond" document identifies the need to monitor, document, and review outcomes of the strategy. It also lists compliance monitoring as a best practice. |  | Self-assessment checklists includes questions about implementation and continuous improvement.
Organizational Integration | References an integrated management systems approach | Requirement to identify interaction with other management systems |  | Shows relationship between asset management and other corporate plans | [7 empty] | Identifies how asset management information can be leveraged for grant writing, setting user fees, tax rates, and developing partnerships for service delivery. |  |  | Outlines other municipal activities that align with asset management, such as infrastructure planning, land use planning, and alternative financing and procurement.
Organizational Plan (High level, not specific to AM) | [8 empty] | Includes a module called "Strategic Goals" which refers to goals at an organizational level - not only specific to asset management. Outlines how to apply Strategic Goals to AM, and what information should be known and documented.
Decision Making and Governance | Describes the relationship between asset management and the asset management system, and how not all the elements that contribute to asset management outcomes can be formalized - such as leadership, culture, motivation, behaviour, etc. Components of the AM system are described. |  | Diagram that illustrates the relationship between key elements of an asset management system and the boundary of systems. | [5 empty] | Includes module on "evaluating decision processes". Outlines the need to document decision processes and benefits from documentation. Identifies process for evaluating decision making processes and key objectives for decision processes. | Includes a recommendation to develop governance structures to support asset management practices |  |  |  | "Informed decision making" sheet outlines process for evaluating decision making processes and improving them.
Document Access (Do you have to pay for it?) | Yes - fill in cost here | YES | YES | NO | NO | NO | NO | NO | NO | NO | YES | NO | NO |  |  | NO
Other Notes |  |  |  | Includes case studies of successful implementations. | Also includes information on collecting O&M related data, such as customer data and performance data | Provides hypothetical examples for application of the top-down and bottom up approaches. | Includes case studies of three organizations that have defined levels of service and the benefit obtained from defining levels of service. | Includes stories of best and worst practices from various sizes of municipalities on infrastructure and public consultation | Good intro information on many components of asset management, but can be difficult to understand how it all fits together. | document may be an effective high level overview on asset management for general audiences. | IIMM is being updated for late 2015 and new edition will be available. | Accompanied with a video that can be a useful communication tool |  |  | Focus is on the contents of the asset management plan. | General comments: black-box, subscription fees
T
key focus of document
topic is covered
some mention
no mention